## MilestonePlan
| Concept | Prototype | Alpha | Beta | Final
| Prototype | Alpha | Pre-Beta | Beta | Gold Master
| 17.11.2017 | 01.12.2017 | 22.12.2017 | 12.01.2018 | 19.01.2018
Character Controller | 1 | 1 | 1 | 1 | 1
Animation (Locomotion, Battle,…) | 1 | 1 | 1 | 1 | 1
User Interface |  |  | 1 | 1 | 1
Interact (Text-Box, Pickup) |  |  | 1 | 1 | 1
Leveldesign (Artist Zeugs) | 1 | 1 | 1 | 1 | 1
Jump & Run |  | 1 | 1 | 1 | 1
Sound (FMOD) |  | 1 | 1 | 1 | 1
Simple Combat (destroy objects) |  |  |  | 1 | 1
Rune Labyrinth |  |  | 1 | 1 | 1
Rune Jump & Run |  |  | 1 | 1 | 1
(Rune Puzzle)? |  |  | 1 | 1 | 1
Note on A4: HI :D

## Definitions
Features
Status | Definition
Concept | The feature is designed.
Prototype | The feature is partially implemented and testable by the developers. The base system for it is implemented and technical questions have been answered.
Alpha | The feature is fully testable and feature complete in-game. Visuals may still be placeholders and major bugs may be present.
Beta | The feature is functionally complete and all major components work in-game. There might be some minor bugs which impact the game flow.
Final | The feature works properly and is polished. Only a few minor bugs might occur which do not impact the game flow. It has reached target quality.
Assets
Status | Definition
Concept | There is some visual reference (either reference art, concepts, scribbles, etc.) for the asset.
Prototype | The asset is in an early WIP state.
Alpha | The asset is partially done. Certain parts are still WIP (textures, materials, animations, etc.). No Sounds yet.
Beta | The asset is done, but has not reached the target quality yet (polishing needed). Includes Sounds.
Final | The asset is polished and fulfills target quality.